## Sheet1
Department: |  | NC Department of Public Safety | [7 empty] | Department: | NC Department of Public Safety
Report Date: |  | for June 2018 | [7 empty] | Report Date: |  | for June 2018
Projects managed by Central Engineering
Projects managed by National Guard
Projects managed by State Highway Patrol
CAPITAL IMPROVEMENT PROJECTS REPORT | [9 empty] | CAPITAL IMPROVEMENT PROJECTS REPORT | [6 empty] | CAPITAL IMPROVEMENT PROJECTS REPORT
Project Identification | [5 empty] | Current Construction Phase |  |  |  | Funding and Sources |  |  | Adequacy of Funding |  |  | Comments | For new capital projects only (Estimate operating costs for the first five FYs of operation.)
# | NEW Budget Code | NEW Fund Code | OC-25 # or SCO Project ID# | Project Title | R&R Project? (Y/N) | Land Acquisition | Design Stages (Pick one from dropdown) | Construction Stage (Pick % complete from dropdown) | Projected Completion Date from Current Project Phase (Enter mo.&yr: XX/20XX) | Amt Expended Project to Date | Primary Funding Source (Pick one from dropdown) | Secondary Funding Source (Pick one from dropdown) | Is the project adequately funded? (Y/N) | How do current cost estimates compare to the project's initial authorized budget? | Will scope reductions be necessary to complete the project within its initial authorized budget? (Y/N) | Notes/Comments | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Source of Funds
1 | 40091 | 4A02 | NA | NG REFORESTATION - CAMP BUTNER | No |  | - |  | ONGOING | 109360.47 | Receipts |  | Yes | On budget | No | Timber Reserve - transfer from 4097 as needed and approved
2 | 40091 | 4A03 | NA | NG UNALLOCATED RECEIPT FUND | No | - |  |  | ONGOING | 653886 | Receipts |  |  |  |  | Other sales of Goods of Public (Timber Sales) - transfer funds as needed and approved by the Secretary to project 4014 and budget code 14550
3 | 40468 | 4C01 |  | NG KITCHEN HOOD PHASE III | Yes | - | Final Drawings/Bid (FD) | 76%-100% | ONGOING | 663919 | General Fund |  | Yes | On budget | No | Multiple Locations
4 | 40569 | 4D01 | 04C617101 | JJ SECURITY CAMERAS YDC (JO 3202) | Yes | - | - | Complete | 05/2017 | 2576161.32 | General Fund |  | No | On budget | Yes | Juv. Justice is working a Master Plan to match facilities with future needs. Evaluating additional needs.
5 | 40569 | 4D05 | 11-08921-01A | AC - GEN RENOV DART CHERRY (JO 2490) | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 08/2017 | 376699 | General Fund | - | Yes | On budget | No | Funds have been used for a major shower renovation, electrical modifications and preliminary work on a new maintenance repair and storage area being performed by Regional Maintenance.
6 | 40569 | 4D06 | 20071001452 | AC - SPILL PREVENTION STATE | Yes |  | Construction Drawings (CD) | 51-75% | 12/2017 | 759061 | General Fund |  | Yes | On budget | No | Some site modifications complete with others in design phase; conversion to Natural Gas will allow some fuel oil storage to be eliminated; funds will be used for recurring 5-year SPCC Plan updates and continued remediation at Central Prison
7 | 40692 | 4E06 | 200710014519 | AC - FIRE & LIFE SAFETY PROJ | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 605478 | General Fund |  | Yes | On budget | No | Funds have been used for 20 projects - 1 in progress. The projects completed include fire alarm systems, electrical panel upgrades and generators and TVSS equipment
8 | 40692 | 4E07 | 200710014513 | AC - KITCH HOOD SUPP SYS UPGR | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 120531 | General Fund |  | Yes | On budget | No | Funds have been used for 6 projects - 4 completed and 2 in progress. These are code required upgrades to existing hoods.
9 | 40692 | 4E08 | 200710014521 | AC - ROOF REP & REPLACE PROJ | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 963784 | General Fund |  | Yes | On budget | No | Ten projects have been completed. Remaining funds will be used for a smaller repair project.
10 | 40692 | 4E09 | 200710014524 | AC - ENERGY EFF IMPROV PROJECTS | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 494174 | General Fund |  | Yes | On budget | No | Eleven projects have been completed. The remaining projects are under construction by Unit Maintenance.
11 | 40692 | 4E10 | 200710014530 | AC - PERIMETER FENCE SYS UPGR | Yes |  | Final Drawings/Bid (FD) | 51-75% | 07/2017 | 6154535 | General Fund |  | Yes | On budget | No | Funds have been used to complete two projects. A third project is under construction.
12 | 40692 | 4E12 | OC 25 to be revised | AC - BERTIE-ENTRPRS-PREFAB C | No |  | Design Development (DD) | - | on hold | 0 | Receipts | - | Yes | On budget | No | Project will be funded by Correction Enterprise at approved budget when funds are available.
13 | 40692 | 4E13 | 200945100145 | AC - CP HOSP SUPPLMENTL FUNDS | No | - | - | Complete | 12/2017 | 5679682 | General Fund |  | Yes | On budget | No | Work is complete. Warranty period in effect.
14 | 40692 | 4E17 |  | DPS - SAMARCAND TA - UST & SEWER LINES (JO# 3765) | Yes |  | Construction Drawings (CD) | 0-25% | 06/2018 | 14305 | General Fund |  | Yes | On budget | No | Removal of UST and repairs to old sewer lines to allow continued development of the campus
16 | 40798 | 4G03 | 20091001455 | AC - WELFARE-CALEDONIA PROG B | No | - | Design Development (DD) |  | on hold | 720 | Receipts |  | No | On budget | No | Project will be funded by Inmate Welfare Fund at approved budget when funds are available.
17 | 40798 | 4G04 | 20091001458 | AC - WELFARE-CASWELL PROG BLD | No | - | Design Development (DD) |  | on hold | 8120 | Receipts |  | No | On budget | No | Project will be funded by Inmate Welfare Fund at approved budget when funds are available.
18 | 40798 | 4G05 | 200910014524 | AC - FIRE & LIFE SAFETY PROJ | Yes | - | Construction Drawings (CD) | 76%-100% | 12/2017 | 675884 | General Fund |  | Yes | On budget | No | Funds have been used to complete 21 projects. There are 6 active projects ranging from design to construction.
19 | 40798 | 4G06 | 200910014523 | AC -KITCHEN HOOD SUPP SYS UP | Yes |  | Construction Drawings (CD) | 76%-100% | 12/2017 | 139092 | General Fund |  | Yes | On budget | No | Seven hood projects complete, one project in design.
20 | 40798 | 4G08 | 200910014529 | AC - MECHAN SYS RENOV/REPLAC | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 463206 | General Fund |  | Yes | On budget | No | Seven projects have been completed. One additional project to be completed with remaining funds.
21 | 40798 | 4G10 | 200910014513 | AC - ENERGY EFFICIENCY IMPROV | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 498094 | General Fund |  | Yes | On budget | No | Seven projects completed. Two projects in construction stage.
22 | 40799 | 4H02 |  | Palliative Care Unit (JO# 3573) | Yes |  | Design Development (DD) | 0-25% | 01/2018 | 288996 | Debt Financed | General Fund | Yes | On budget |  | Conversion of existing Central Prison facilities for a specialized care unit - design in progress
23 | 44897 | 4K05 |  | Palliative Care Unit (JO# 3574) | Yes |  | Design Development (DD) | 0-25% | 01/2018 | 245265 | Debt Financed | General Fund | Yes | On budget |  | Conversion of existing Central Prison facilities for a specialized care unit - design in progress
25 | 40946 | 4M05 | 20114510002 | AC - KITCHEN HOOD SUPP UNDRAD | Yes |  | Construction Drawings (CD) | 25-50% | 12/2017 | 362425 | Debt Financed | - | Yes | On budget | No | Three projects completed. One in construction.
26 | 40946 | 4M10 |  | Palliative Care Unit (JO# 3575) | Yes |  | Design Development (DD) | 0-25% | 01/2018 | 0 | Debt Financed | General Fund | Yes | On budget |  | Conversion of existing Central Prison facilities for a specialized care unit - demolition and design in progress
27 | 41006 | 4N02 | 200910014510 | AC - WELFARE-SOUTHERN MED BLD | Yes |  |  |  | on hold | 7650 | Receipts |  |  |  |  | Project funded by Inmate Welfare Fund on hold pending funding.
28 | 41006 | 4N05 | 20134510011 | AC - R&R KITCHEN HOOD UPGRAD | Yes |  | Construction Drawings (CD) | 0-25% | 12/2017 | 151994 | General Fund |  | Yes | On budget | No | One project designed and construction beginning. One project identified and under contract for design.
29 | 41006 | 4N06 | 20134510018 | AC - R&R FIRE & LIFE SAFETY | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 68454 | General Fund |  | Yes | On budget | No | Six projects completed. Balance assigned to Piedmont CI Elevator R&R
30 | 41006 | 4N07 | 20134510013 | AC - ROOF REPAIRS & REPLACE | Yes |  | Final Drawings/Bid (FD) | Complete | 12/2017 | 169122 | General Fund |  | Yes | On budget | No | Four projects complete. Balance will be used for small projects
31 | 41207 | 4U08 | 120895701 | JJ Track & Field Facility - Stonewall Jackson YDC (JO 3223) | Yes | - | Construction Drawings (CD) | 0-25% | 12/2017 | 153295 | Receipts |  | Yes | Over budget | Yes | Work is complete as far as funding available. Warranty period.
32 | 41207 | 4U09 | 20134510011 | AC Kitchen Hood Upgrade | Yes | - | Final Drawings/Bid (FD) | 51-75% | 12/2017 | 502317 | General Fund |  | Yes | On budget | No | Two projects under construction. Three complete.
33 | 41207 | 4U10 | 20134510017 | AC Obsolete Electronic Systems | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 1164605 | General Fund |  | Yes | On budget | No | Seven projects completed. One project in progress.
34 | 41207 | 4U11 | 20134510018 | AC Fire & Life Safety Projects | Yes | - | Construction Drawings (CD) | 25-50% | 12/2017 | 960581 | General Fund |  | Yes | On budget | No | Three projects in progress at different stages from design to construction. Five projects complete.
35 | 41207 | 4U12 | 20134510019 | AC CP Elevators (JO 3245) | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 01/2018 | 1053220 | General Fund |  | Yes | On budget | No | Initial upgrades complete. Funding to be used for upgrades to MH East & West elevators.
36 | 41207 | 4U13 | 20134510013 | AC Roof Repair & Replacement | Yes | - | Construction Drawings (CD) | 51-75% | 12/2017 | 1420554 | General Fund |  | Yes | On budget | No | Fourteen Projects completed. Four other projects in progress.
37 | 41207 | 4U14 | 201345100110 | AC Mechanical Systems Renov. & Replace. | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 1421839 | General Fund |  | Yes | On budget | No | Thirteen Projects completed. Two projects in progress at different stages of construction.
38 | 41207 | 4U15 | 20134510011 | AC Water/Wastewater Improvements | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 771602 | General Fund |  | Yes | On budget | No | Systems upgrade at as many facilities as funding will support. Some have been designed by CE staff while others are by contract. Construction is through a combination of CM&M (ICP), Regional Maintenance and/or contract.
39 | 41207 | 4U16 | 20134510012 | AC DART Cherry Renovations (JO 3288) | Yes | - | Construction Drawings (CD) | 76%-100% | 12/2017 | 73547 | General Fund |  | Yes | On budget | No | Restoration project to restore space in an existing building to use as a maintenance shop, storage and general purposes.
40 | 41207 | 4U17 | 20134510014 | AC Energy Efficiency Impv. Projects | Yes | - | Final Drawings/Bid (FD) | 51-75% | 12/2017 | 523761 | General Fund |  | Yes | On budget | No | One project completed. Seven projects in progress.
41 | 41207 | 4U24 | 20115120114 | JJDP YDC Security Cameras & Surveillance | Yes | - | Design Development (DD) | Complete | 12/2017 | 886774 | General Fund |  | Yes | On budget | No | Work has been completed at CA Dillon YDC and Pitt JD, Dobbs and Stonewall Jackson YDC. ECS working at Cumberland JDC & Alexander - Balance will be used for another small project
42 | 41207 | 4U26 | 20115120113 | JJDP YDC Safety & Security Systems | Yes | - | Final Drawings/Bid (FD) | 51-75% | 12/2017 | 160716 | General Fund |  | Yes | On budget | No | Three projects complete and one in progress.
43 | 41207 | 4U27 |  | NG Fire Alarm Systems - Phase 2 | Yes |  | Design Development (DD) | Complete | 06/10/2015 | 57319 | General Fund |  | Yes | On budget | No | Awaiting final walkthrough
44 | 41207 | 4U30 |  | SHP Training Academy Bldg. 10 (JO 3376) | Yes | - | - | Complete | Warranty | 997918 | General Fund |  | Yes | On budget | No | Initial renovations complete - looking at additional needs to utilize funds.
45 | 41207 | 4U31 |  | Samarcand - Sewer System (JO# 3761) | Yes | - | Final Drawings/Bid (FD) | 0-25% | 12/2017 | 167926 | General Fund |  | Yes | On budget | No | Repair/replace old sewer lines at Academy
46 | 41207 | 4U32 |  | CA Dillon Cottage E Reno | Yes | - | Design Development (DD) | 0-25% |  | 0 | General Fund |  | No |  |  | Project still being planned.
47 | 44365 | 4B02 | NA | JJ DOBBS COTT/GYM/SCH HVAC (JO 3203) | Yes |  | - | Complete | on hold | 263088 | Debt Financed |  | Yes | On budget | No | Juv. Justice is working a Master Plan to match facilities with future needs. Evaluating additional needs.
48 | 44365 | 4B04 | 200510014516 | AJ - FIRE & LIFE SAFETY | Yes |  | Final Drawings/Bid (FD) | 51-75% | 12/2017 | 1754580 | Debt Financed | - | Yes | On budget | No | Funded replacement of Fire Alarm Systems & Fire Protection Systems at Central Prison and other facilities. Five projects in progress. Seven complete.
| 44365 | 4B05 | 200510014517 | AJ - ROOF REPAIRS & REPLACE | Yes |  | Final Drawings/Bid (FD) | 0-25% | ONGOING | 4729053 | Debt Financed | - | Yes | On budget | No | Multiple Locations completed. Two projects to be completed.
49 | 44365 | 4B06 |  | NG FIRE ALARM SYSTEMS - PHASE II | Yes | - | Final Drawings/Bid (FD) | 51-75% | 12/2015 | 1080245 | Debt Financed |  | Yes | On budget | No | Design complete. All current projects Construction awarded.
50 | 44896 | 4J01 | 20091005452 | AJ - BROUGHTON STEAM PLT-ENT (JO 2891) | Yes |  | Construction Drawings (CD) | 0-25% | 06/2017 | 3093064 | Receipts |  | Yes | On budget | No | Construction is complete and closed. Last time on report.
51 | 44896 | 4J04 | OC 25 to be revised | AJ - TABOR INDUSTRY UPFIT-ENT (JO 3595) | No |  | Final Drawings/Bid (FD) | 76%-100% | 05/2018 | 769254 | Receipts |  | Yes | On budget | No | Procurement for construction underway. Construction began December, 2017.
52 | 44896 | 4J05 |  | NG - Master Plan Statewide Ph 2 | Yes | - | Design Development (DD) | 51-75% | ONGOING | 614425 | General Fund | - | Yes | - | No | Ongoing designs for all HUBs
53 | 41307 | 4R18 |  | NG Projects | Yes | - | Final Drawings/Bid (FD) |  |  | 0 | General Fund
54 | 41307 | 4R19 | 13-09999-04 A | NG - Wilmington Building Expansion | Yes |  | Final Drawings/Bid (FD) | 0-25% | on hold | 103706 | General Fund | Receipts | Yes | On budget |  | Under design contract/Construction cancelled
55 | 41307 | 4R20 | 13-09999-04 B | NG - Wilmington Site Expansion |  |  | Final Drawings/Bid (FD) | Complete | 2017-01-01 | 990141 | General Fund | Receipts | Yes | On budget |  | Complete
56 | 41307 | 4R21 | 13-09999-02 E | NG - Nashville Building Expansion | Yes |  | Final Drawings/Bid (FD) | 0-25% | 2018-12-01 | 898334 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
57 | 41307 | 4R22 | 13-09999-02 F | NG - Nashville Site Expansion |  |  | Final Drawings/Bid (FD) | 0-25% | 2017-01-01 | 107506 | General Fund | Receipts | Yes | On budget |  | Under design contract. Will award construction contract next quarter.
58 | 41307 | 4R23 | 13-09999-04 C | NG - Clinton Building Expansion | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 2018-12-01 | 1184534 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
59 | 41307 | 4R24 | 13-09999-04 D | NG - Clinton Site Expansion |  |  | Final Drawings/Bid (FD) | 76%-100% | 2017-01-01 | 991610.46 | General Fund | Receipts | Yes | On budget |  | Complete
60 | 41307 | 4R25 | 13-09999-01 E | NG - Salisbury Building Expansion | Yes |  | Final Drawings/Bid (FD) | 0-25% | 2018-12-01 | 1108795 | General Fund | Receipts | Yes | On budget |  | Completed final walk through.
61 | 41307 | 4R26 | 13-09999-01 F | NG - Salisbury Site Expansion |  |  | Final Drawings/Bid (FD) | 51-75% | 2017-01-01 | 999089 | General Fund | Receipts | Yes | On budget |  | Waiting on final invoice
62 | 41307 | 4R27 | 13-09999-01 C | NG - Parkton Building Expansion | Yes |  | Final Drawings/Bid (FD) | 0-25% | 2018-12-01 | 928736 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
63 | 41307 | 4R28 | 13-09999-01 D | NG - Parkton Site Expansion |  |  | Final Drawings/Bid (FD) | 0-25% | 2018-12-01 | 514285 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
64 | 41307 | 4R29 | 13-09999-02 C | NG - Benson Building Expansion | Yes |  | Final Drawings/Bid (FD) | 0-25% | 2018-12-01 | 128030 | General Fund | Receipts | Yes | On budget |  | Under design contract.
65 | 41307 | 4R30 | 13-09999-02 D | NG - Benson Site Expansion |  |  | Final Drawings/Bid (FD) | 0-25% | 2018-12-01 | 98856 | General Fund | Receipts | Yes | On budget |  | Under design contract.
66 | 41307 | 4R31 | 13-09999-03 D | NG - Charlotte Building Expansion | Yes |  | Final Drawings/Bid (FD) | complete | 2015-10-19 | 1169779.23 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
67 | 41307 | 4R32 | 13-09999-01 A | NG - Asheboro Site Expansion |  |  | Final Drawings/Bid (FD) | 76%-100% | 2017-01-01 | 1028351 | General Fund | Receipts | Yes | On budget |  | complete
68 | 41307 | 4R33 | 13-09999-01 G | NG - Winston-Salem Building Expansion | Yes |  | Final Drawings/Bid (FD) | Complete | 2016-11-01 | 1207292 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
69 | 41307 | 4R34 | 13-09999-01 H | NG - Winston-Salem Site Expansion |  |  | Final Drawings/Bid (FD) | 76%-100% | 2016-11-01 | 1108111.57 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
70 | 41307 | 4R35 | 13-09999-03 B | NG - Concord Building Expansion | Yes |  | Final Drawings/Bid (FD) | Complete | 2017-01-01 | 1197321 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
71 | 41307 | 4R36 | 13-09999-03 C | NG - Concord Site Expansion |  |  | Final Drawings/Bid (FD) | 76%-100% | 2016-12-01 | 996985 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
72 | 41307 | 4R37 | 13-09999-01 B | NG - Burlington Site Expansion |  |  | Final Drawings/Bid (FD) | Complete | 2015-09-01 | 1195729 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
73 | 41307 | 4R38 | 13-09999-03 A | NG - Albemarle Site Expansion |  |  | Final Drawings/Bid (FD) | Complete | 2017-01-01 | 1171905 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
74 | 41307 | 4R39 | 13-09999-03 E | NG - Belmont Building Rehab | Yes |  | Final Drawings/Bid (FD) | 0-25% | on hold | 123968 | General Fund | Receipts | Yes | On budget |  | Under design contract.
75 | 41307 | 4R40 | 13-09999-04 E | NG - Beulaville Building Expansion | Yes |  | Final Drawings/Bid (FD) | 0-25% | 2018-12-01 | 677329 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
76 | 41307 | 4R41 | 13-09999-05 | NG - Boone Building Expansion | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 2016-12-01 | 1161417 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
77 | 41307 | 4R42 | 13-09999-02 B | NG - Dunn Building Expansion | Yes |  | Final Drawings/Bid (FD) | Complete | 2017-08-01 | 115982 | General Fund | Receipts | Yes | On budget |  | Awaiting federal construction funding
78 | 41307 | 4R43 | 13-09999-02 A | NG - Durham Building Expansion | Yes | - | Final Drawings/Bid (FD) | Complete | 2016-05-01 | 1188577 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
79 | 41307 | 4R44 | 20137092011 | AJ - Kitchen Hood Suppression Systems | Yes | - | Construction Drawings (CD) | 51-75% | 2017-12-01 | 397661 | General Fund |  | Yes | On budget | No | Five projects identified. Two complete and others in various stages of construction
80 | 41307 | 4R45 | 20137092012 | AJ - Replace/Upgrade Obsolete Electronic Systems | Yes | - | Construction Drawings (CD) | 25-50% | 2017-12-01 | 1759487 | General Fund |  | Yes | On budget | No | Ten projects identified. Six completed and work has begun on 4 other projects.
81 | 41307 | 4R46 | 20137092013 | AJ - Fire & Life Safety Systems | Yes | - | Design Development (DD) | 0-25% | 2017-12-01 | 1476527 | General Fund |  | Yes | On budget | No | Nineteen projects funded. Eight completed. Ten in design or construction. One cancelled.
82 | 41307 | 4R47 | 20137092014 | AJ - Roof Repair & Renovation | Yes | - | Construction Drawings (CD) | 51-75% | 2017-12-01 | 5658134 | General Fund |  | Yes | On budget | No | Eighteen projects identified. Six completed. Twelve in progress our under design.
83 | 41307 | 4R48 | 201370920117 | AJ - Architectural Systems | Yes | - | Design Development (DD) | 0-25% | 2017-12-01 | 116809 | General Fund |  | Yes | On budget | No | Ten projects completed with 8 in progress and remainder in design.
84 | 41307 | 4R49 | 20137092022 | AJ - Juvenile Justice Strategic Plan | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 2017-12-01 | 1636667 | General Fund |  | Yes | On budget | No | Implementation of Long Range Strategic Plan - renovations at Stonewall Jackson and expansions at Lenoir, Edgecombe and Chatham. SJ/McWhorter complete; Edgecombe & Lenoir in warranty phase; Chatham on hold.
85 | 41307 | 4R50 | 201349400410 | NG - Reno to Improve Existing | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 2016-09-30 | 1834390 | General Fund | Receipts | Yes | On budget
86 | 41307 | 4R51 | 201349400411 | NG - Mechanical System Reno | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 2016-09-30 | 1513008 | General Fund | Receipts | Yes | On budget
87 | 41307 | 4R52 | 201349400412 | NG - Fire & Lyfe Safety Systems | Yes | - | Final Drawings/Bid (FD) | Complete | 2016-04-30 | 218540 | General Fund | Receipts | Yes | On budget
88 | 41307 | 4R55 | 20134940049 | NG - Underground Storage | Yes | - | Design Development (DD) | 0-25% | 2017-06-01 | 19498 | General Fund | Receipts | Yes
89 | 41307 | 4R56 | 201349400421 | NG - Security Systems | Yes | - | Construction Drawings (CD) | 0-25% | 2015-02-01 | 17624 | General Fund | Receipts | Yes
90 | 41307 | 4R59 | 20134940031 | SHP - Laurinburg Office Renovations | Yes | - | - | Complete | 2016-10-01 | 42000 | General Fund |  | Yes | On budget | No | Work is complete. Warranty period in effect.
91 | 41307 | 4R61 | 20113650029 | SBI - Bldg. 9 Renovations (JO 3490) | Yes | - | Final Drawings/Bid (FD) | Complete | 2016-05-01 | 1092850 | General Fund |  | Yes | On budget |  | Work complete - warranty period.
92 | 41307 | 4R62 | 201341101345 | SBI - Bldg. 16 Renovations (JO 3491) | Yes | - | Design Development (DD) | 0-25% | 2016-08-01 | 438037 | General Fund |  | Yes | On budget |  | Design is complete. Awaiting funding for construction to begin
93 | 41407 | 4T02 |  | Caledonia Grain Bin (JO # 3469) | No | - | Design Development (DD) |  | 2017-12-01 | 1044794 | Receipts |  | Yes | On budget |  | Installation complete - awaiting grain harvest and final calibrations
94 | 41407 | 4T03 |  | Maury Industry Upfit | No | - |  |  | on hold | 0 | Receipts |  | Yes | On budget |  | Scope has not been defined by owner
95 | 41446 | 4S01 | 20157092001 | AJ - Samarcand Training Academy (JO 3503) | Yes | - | Construction Drawings (CD) | 76%-100% | 2017-12-01 | 5172949 | Debt Financed |  | Yes | On budget |  | This phase complete. Fund to be closed this quarter.
96 | 41446 | 4S02 | 20157092014 | AJ - Replace/Upgrade Obsolete Electronic Systems | Yes | - | Construction Drawings (CD) | 25-50% | 2017-12-01 | 497525 | Debt Financed |  | Yes | On budget |  | One project complete. One designed and in procurement.
97 | 41446 | 4S03 | 201370920129 | AJ - Mechanical Systems R&R | Yes | - | Design Development (DD) | 0-25% | 2017-12-01 | 872853 | Debt Financed |  | Yes | On budget |  | Seven projects completed. Seven projects defined and in design.
98 | 41446 | 4S04 | 201370920135 | AJ - Fire & Life Safety | Yes | - | Design Development (DD) | 0-25% | 2017-12-01 | 2391 | Debt Financed |  | Yes | On budget |  | Two projects defined and in design.
99 | 41446 | 4S05 | 201370920128 | AJ - Roof Repair & Replacement | Yes | - | Design Development (DD) | 0-25% | 2017-12-01 | 235138 | Debt Financed |  | Yes | On budget |  | Four projects defined. Three complete.
100 | 41446 | 4S06 | 201370920136 | AJ - Architectural Systems | Yes | - | Design Development (DD) | 0-25% | 2017-12-01 | 151830 | Debt Financed |  | Yes | On budget |  | Three projects completed. Four projects in design.
101 | 41446 | 4S07 | 201370920130 | AJ - Asbestos Abatement & Haz. Mat. | Yes | - | Design Development (DD) | 0-25% | 2017-12-01 | 108730 | Debt Financed |  | Yes | On budget |  | Nine projects complete. One in progress.
102 | 41507 | 4Q01 |  | AC - Palliative Care Unit (JO 3572) | Yes | - | Design Development (DD) | 0-25% | 01/2018 | 20600 | General Fund | General Fund | Yes | On budget |  | Conversion of existing Central Prison facilities for a specialized care unit - design in progress
103 | 41507 | 4Q02 | 3720160122 | NG-Armory & Facility Development |  | - |  |  |  | 159276 | General Fund
104 | 41507 | 4Q04 | 20157092014 | AJ - Replace/Upgrade Obsolete Electronic Systems | Yes | - | Final Drawings/Bid (FD) | 25-50% | 01/01/2018 | 1246998 | General Fund |  | Yes | On budget |  | Three projects complete. Six projects designed and beginning installation
105 | 41507 | 4Q05 | 201370920135 | AJ - Fire & Life Safety Systems | Yes | - | Design Development (DD) | 0-25% | 07/01/2018 | 262520 | General Fund |  | Yes | On budget |  | Thirteen projects defined and in design
106 | 41507 | 4Q06 | 201370920136 | AJ - Architectural Systems | Yes | - | Design Development (DD) | 0-25% | 07/01/2018 | 19383 | General Fund |  | Yes | On budget |  | Nine projects defined and in design
107 | 41507 | 4Q07 | 201370920130 | AJ - Asbestos Abatement & Haz. Mat. | Yes | - | Design Development (DD) | 0-25% | 07/01/2018 | 300000 | General Fund |  | Yes | On budget |  | Last time on report. Funds exhausted.
108 | 41507 | 4Q08 | 201370920131 | AJ - Water & Wastewater Treatment | Yes | - | Design Development (DD) | 0-25% | 07/01/2018 | 345198 | General Fund |  | Yes | On budget |  | Three projects defined and in design
109 | 41507 | 4Q09 | 201370920133 | AJ - Energy Efficiency Projects | Yes | - | Design Development (DD) | 0-25% | 07/01/2018 | 2348 | General Fund |  | Yes | On budget |  | One project defined and in progress
110 | 41507 | 4Q10 | 20157092013 | AJ - Kitchen Hood Suppression Systems | Yes | - | Design Development (DD) | 0-25% | 07/01/2018 | 0 | General Fund |  | Yes | On budget
111 | 41507 | 4Q11 | 20137092019 | AJ - Underground Storage Tanks | Yes | - | Design Development (DD) | 0-25% | 07/01/2018 | 56474 | General Fund |  | Yes | On budget |  | Contract issued for site analysis to remove tanks as funding allows.
112 | 41507 | 4Q12 | 20157092012 | AJ - Demolition of Abandoned Bldgs | Yes | - | Design Development (DD) | 0-25% | 07/01/2018 | 79300 | General Fund |  | Yes | On budget |  | Two projects defined and in progress
113 | 41507 | 4Q13 | 20157092011 | AJ - Paving Repairs, Chase Roads, etc. | Yes | - | Design Development (DD) | 0-25% | 07/01/2018 | 119932 | General Fund |  | Yes | On budget |  | Three projects identified and in design stage.
114 | 41507 | 4Q14 | 201370920134 | AJ - Security Fencing | Yes | - | Design Development (DD) | 0-25% | 07/01/2018 | 146 | General Fund |  | Yes | On budget
115 | 41507 | 4Q15 | 201370920522 | NG-Renovate - Improve Space | Yes | - |  |  |  | 89503 | General Fund |  | Yes | On budget
116 | 41507 | 4Q16 | 201370920525 | NG-Fire & Life Safety Systems | Yes | - |  |  |  | 0 | General Fund |  | Yes | On budget
117 | 41507 | 4Q17 | 201370920523 | NG-Electrical, Plumbing & HVAC | Yes | - |  |  |  | 81427 | General Fund |  | Yes | On budget
118 | 41507 | 4Q18 | 201370920521 | NG-Roof Repair & Replacement | Yes | - |  |  |  | 224694 | General Fund |  | Yes | On budget
119 | 41507 | 4Q19 | 201370920524 | NG-Asbestos Abatement & Haz. Mater. | Yes | - |  |  |  | 8838 | General Fund |  | Yes | On budget
120 | 41507 | 4Q20 | 20137092043 | EM - Badin Warehouse - LT Access & Paving (JO 3616) | Yes | - | Design Development (DD) | 0-25% | 07/01/2018 | 19787 | General Fund |  | Yes | On budget |  | Contracting for Civil Eng. Evaluation & recommendation
121 | 41507 | 4Q21 | 201149400312 | SHP - Lincolnton Office | Yes | - | Final Drawings/Bid (FD) | 76%-100% |  | 34439 | General Fund |  |  |  |  | This project complete. Remaining funds to be used for special project approved by OSBM.
122 | 41507 | 4Q22 | 20114940034 & 201149400311 | SHP - Fuel Master Monitors |  | - |  | 51-75% |  | 365187 | General Fund |  |  |  |  | 85% complete. Remaining sites should be complete within 60 days.
123 | 41507 | 4Q23 |  | AJ - Nash CI - Generator Replacement (JO 3627) | Yes | - | Construction Drawings (CD) | 51-75% | 07/01/2018 | 2542418 | General Fund |  | Yes | On budget |  | Installation of generators in progress
124 | 41507 | 4Q24 | 201370920129 | AJ - Mechanical Systems R&R | Yes | - | Design Development (DD) | 0-25% | 07/01/2018 | 1336141 | General Fund |  | Yes | On budget |  | Fifteen projects definded. Two complete and 13 under design and/or construction
125 | 41507 | 4Q25 | 201370920128 | AJ - Roof Repair & Replacement | Yes | - | Design Development (DD) | 0-25% | 07/01/2018 | 986733 | General Fund |  | Yes | On budget |  | Ten projects identified. One complete and nine in various planning or intallation stages.
126 | 41507 | 4Q26 | 16-16096-01 | NG-Armory & Facility Development - Eli | No | - |  |  |  | 277128 | General Fund | Receipts | Yes | On budget
127 | 41507 | 4Q27 | 16-16095-01 | NG-Armory & Facility Development - Jac | No | - |  |  |  | 338015 | General Fund | Receipts | Yes | On budget
128 | 41607 | 4601 | 20177092012 | AJ - Nash Print Plant Roof Repl. (JO# 3683) | Yes | - | Design Development (DD) | 51-75% | 07/01/2018 | 658012 | Receipts |  | Yes | On budget |  | Replacement of the Print Plant Roof funded by Correction Enterprise. To be coordinated with other roof work at Nash CI
| 41607 | 4602 | 20177092013 | AJ - Harnett Visitor Center (JO# 3682) | Yes | - | Design Development (DD) | - | 07/01/2018 | 25602 | Receipts |  | Yes | On budget |  | Visitor center to be added as part of perimeter fence replacement. Funded through Inmate Welfare.
| 41607 | 4604 | 16-16096-01 | NG - Armry & Fclty Dev - Eliz |  | - |  |  |  | 0 | General Fund | Receipts | Yes | On budget
129 | 41607 | 4605 | 16-16095-01 | NG - Armry & Fclty Dev - JAC |  | - |  |  |  | 0 | General Fund | Receipts | Yes | On budget
130 | 41607 | 4606 |  | NG - Armry & Fclty Dev - LOU |  | - |  |  |  | 0 | General Fund | Receipts | Yes | On budget
131 | 41607 | 4607 |  | NG - Armry & Fclty Dev - REIDS |  | - |  |  |  | 0 | General Fund | Receipts | Yes | On budget
132 | 41607 | 4608 | 201370920527 | NG - Helipad Planning |  | - |  |  |  | 0 | General Fund | Receipts | Yes | On budget
133 | 41607 | 4609 |  | NG - Camp Butner Land Purchase |  | - |  |  |  | 186025 | General Fund | Receipts | Yes | On budget
134 | 41607 | 4610 |  | NG - Wilkes Cty Armory Sup |  | - |  |  |  | 0 | General Fund | Receipts | Yes | On budget
135 | 41607 | 4611 |  | NG - Tarheel Challenge Gym |  | - |  |  |  | 700000 | General Fund | Receipts | Yes | On budget
136 | 41607 | 4612 |  | AJ - Piedmont CI Elevator R&R (JO# 3717) | Yes | - | Design Development (DD) | - | 07/01/2018 | 68396 | General Fund |  | Yes | On budget |  | Critical repairs to continue facility operations.
137 | 41607 | 4613 |  | Caledonia CI - Shower & Bath R&R (JO# 3725) | Yes | - | Final Drawings/Bid (FD) | Complete | 07/01/2018 | 75139 | General Fund |  | Yes | On budget |  | Repairs have begun
138 | 41607 | 4614 |  | AJ - Energy Efficiency Projects | Yes | - |  |  | 07/01/2018 | 0 | General Fund |  | Yes | On budget
139 | 41607 | 4615 |  | SBI/SHP - Renovate Perimeter (JO# 3718) | Yes | - | Design Development (DD) | - | 07/01/2018 | 48290 | General Fund |  | Yes | On budget |  | These three projects will improve overall conditions at the Garner Road Campus housing the State Highway Patrol Training Academy and offices for the State Bureau of Investigation
140 | 41607 | 4616 |  | SHP/SBI - Roadway & Access (JO# 3719) | Yes | - | Design Development (DD) | - | 07/01/2018 | 0 | General Fund |  | Yes | On budget
141 | 41607 | 4617 |  | SHP/SBI - Partial Infrastructure Rehab (JO# 3720) | Yes | - | Design Development (DD) | - | 07/01/2018 | 0 | General Fund |  | Yes | On budget
142 | 41607 | 4618 |  | SHP - Update Fuel Facilities |  | - | Design Development (DD) | 51-75% |  | 423830 | General Fund |  |  |  |  | 85% complete. Remaining sites should be complete within 60 days.
143 | 41607 | 4619 |  | NG - Fire & Life Safety Systems |  | - |  |  |  | 0 | General Fund | Receipts | Yes | On budget
144 | 41607 | 4620 |  | NG - Asbestos, Lead PN |  | - |  |  |  | 57056 | General Fund | Receipts | Yes | On budget
145 | 41607 | 4621 |  | AJ - Epoxy Flooring | Yes | - | Construction Drawings (CD) | 25-50% |  | 82122 | General Fund |  | Yes |  |  | Excess funding from 41607-4613 to be used at other AJ facilities
146 | 46607 | 4W01 |  | AJ - Samarcand Trng. Academy (JO 3651) | Yes | - | Construction Drawings (CD) | 0-25% | 07/01/2018 | 3149388 | Debt Financed |  |  |  |  | Renovations continue
147 | 46607 | 4W02 |  | NG - Guilford Readiness Center | Yes | - |  |  |  | 0 | Debt Financed | Receipts | Yes
148 | 46607 | 4W03 |  | NG - Burke Readiness Center | Yes | - |  |  |  | 925462 | Debt Financed | Receipts | Yes
149 | 46607 | 4W04 |  | NG - Wilkes Readiness Center | Yes | - |  |  |  | 0 | Debt Financed | Receipts | Yes
150 | 41707 | 4701 |  | SHP - Greenville Office Bldg & Garage |  | - |  |  |  | 2000000 | General Fund |  |  |  |  | Project will be handled by DOT under MOU
151 | 41707 | 4702 |  | AJ - YDC in Rockingham County | No | Price negotiations | Design Development (DD) |  |  | 109525 | General Fund |  | No | Under budget |  | Site to be indentified for facility. Project funded without location or construction design and estimate
152 | 41707 | 4703 |  | AJ - Stonewall Jackson YDC - Fence | Yes | - | Design Development (DD) | 25-50% |  | 97181 | General Fund |  | Yes | On budget |  | Construction underway
153 | 41707 | 4704 |  | NG - JFHQ Helipad | No | - | - |  |  | 0 | General Fund | -
154 | 41707 | 4705 |  | NG - DuPont Forest Joint Training Ctr. | No | - | - |  |  | 0 | General Fund | -
155 | 41707 | 4706 |  | AJ- Convert Bldgs. @ Swannanoa CCW for Female CRV | Yes | - | Design Development (DD) | 0-25% |  | 62094 | General Fund |  | Yes | On budget |  | Design in progress to meet requirements and code compliance. Put on hold to consider alternatives.
156 | 41707 | 4707 |  | NG - Demolition of Western Youth High Rise | Yes | - | - |  |  | 0 | General Fund | -
157 | 41707 | 4709 |  | AJ - Obstacle Course @ Samarcand | No | - | Design Development (DD) |  |  | 11643 | General Fund |  | Yes | On budget |  | Design to be contracted outside Central Engineering
158 | 41707 | 4710 |  | AJ - Elevator Repair & Renovation | Yes | - | Design Development (DD) |  |  | 22978 | General Fund |  | Yes | On budget |  | Design to be contracted outside Central Engineering
159 | 41707 | 4711 |  | AJ Replace & Upgrade Obsolete Electronics | Yes | - | Design Development (DD) | 0-25% |  | 121209 | General Fund |  | Yes | On budget |  | Five projects in design and purchasing
160 | 41707 | 4712 |  | AJ - Security Fencing | Yes | - | Design Development (DD) |  |  | 0 | General Fund |  | Yes | On budget
161 | 41707 | 4713 |  | AJ - Mechanical Systems R&R | Yes | - | Design Development (DD) | 0-25% |  | 4092 | General Fund |  | Yes | On budget |  | Seven projects in design and purchasing
162 | 41707 | 4714 |  | AJ - Fire & Life Safety Systems | Yes | - | Design Development (DD) |  |  | 0 | General Fund |  | Yes | On budget
163 | 41707 | 4715 |  | AJ - Roof Repair & Replacement | Yes | - | Design Development (DD) |  |  | 0 | General Fund |  | Yes | On budget
164 | 41707 | 4716 |  | NG - Roof Repair & Replacement |  | - | - |  |  | 0
165 | 41707 | 4717 |  | SHP - Update Fuel Facilities |  | - | - |  |  | 0 | General Fund
166 | 41707 | 4718 |  | EM - Badin Warehouse - LT Access & Paving | No | - | Design Development (DD) | 0-25% | 09/2018 | 0 | General Fund |  | Yes | On budget |  | on hold for weather
167 | 41707 | 4719 |  | AJ - Safety Improvements | Yes | - | Design Development (DD) | 0-25% |  | 40061 | General Fund |  | Yes | On budget |  | Three systems in design and purchasing
168
169
170

## Sheet2
-
Schematic Design (SD)
Design Development (DD)
Construction Drawings (CD)
Final Drawings/Bid (FD)
-
0-25%
25-50%
51-75%
76%-100%
Complete
-
Yes
No
-
General Fund
Receipts
Debt Financed
Self-Liquidating/Revenue Bonds
-
General Fund
Receipts
Debt Financed
Self-Liquidating/Revenue Bonds
-
On budget
Under budget
Over budget
-
General Fund
Receipt
-
Appraisal
Price negotiations
COS approval process
Closing
Complete