## Sheet1
Department: |  | NC Department of Public Safety | [7 empty] | Department: | NC Department of Public Safety
Report Date: |  | for March 31, 2017 | [7 empty] | Report Date: |  | for March 31, 2017
Projects managed by Central Engineering
Projects managed by National Guard
Projects managed by State Highway Patrol
CAPITAL IMPROVEMENT PROJECTS REPORT | [9 empty] | CAPITAL IMPROVEMENT PROJECTS REPORT | [6 empty] | CAPITAL IMPROVEMENT PROJECTS REPORT
Project Identification | [5 empty] | Current Construction Phase |  |  |  | Funding and Sources |  |  | Adequacy of Funding |  |  | Comments | For new capital projects only (Estimate operating costs for the first five FYs of operation.)
# | NEW Budget Code | NEW Fund Code | OC-25 # or SCO Project ID# | Project Title | R&R Project? (Y/N) | Land Acquisition | Design Stages (Pick one from dropdown) | Construction Stage (Pick % complete from dropdown) | Projected Completion Date from Current Project Phase (Enter mo.&yr: XX/20XX) | Amt Expended Project to Date | Primary Funding Source (Pick one from dropdown) | Secondary Funding Source (Pick one from dropdown) | Is the project adequately funded? (Y/N) | How do current cost estimates compare to the project's initial authorized budget? | Will scope reductions be necessary to complete the project within its initial authorized budget? (Y/N) | Notes/Comments | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Source of Funds
1 | 40091 | 4A02 | NA | NG REFORESTATION - CAMP BUTNER | No |  | - |  | ONGOING | 109360.47 | Receipts |  | Yes | On budget | No | Timber Reserve - transfer from 4097 as needed and approved
2 | 40091 | 4A03 | NA | NG UNALLOCATED RECEIPT FUND | No | - |  |  | ONGOING | 645993.68 | Receipts |  |  |  |  | Other sales of Goods of Public (Timber Sales) - transfer funds as needed and approved by the Secretary to project 4014 and budget code 14550
3 | 40468 | 4C01 |  | NG KITCHEN HOOD PHASE III | Yes | - | Final Drawings/Bid (FD) | 76%-100% | ONGOING | 663919 | General Fund |  | Yes | On budget | No | Multiple Locations
4 | 40569 | 4D01 | 04C617101 | JJ SECURITY CAMERAS YDC (JO 3202) | Yes | - | - | Complete | 05/2017 | 137365.32 | General Fund |  | No | On budget | Yes | Juv. Justice is working a Master Plan to match facilities with future needs. Evaluating additional needs.
5 | 40569 | 4D03 | 200510014542 | AC - ROOF REPAIR REPLACE PROJ | Yes |  | Final Drawings/Bid (FD) | 76%-100% | on going | 674299 | General Fund |  | Yes | On budget | No | Funds used to address 13 projects - 12 complete with one in construction stage.
6 | 40569 | 4D04 | 200510014547 | AC - FIRE & LIFE SAFETY STATE | Yes |  | - | Complete | 11/2017 | 502587 | General Fund |  | Yes | On budget | No | Projects complete.
7 | 40569 | 4D05 | 11-08921-01A | AC - GEN RENOV DART CHERRY (JO 2490) | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 08/2017 | 376699 | General Fund | - | Yes | On budget | No | Funds have been used for a major shower renovation, electrical modifications and preliminary work on a new maintenance repair and storage area being performed by Regional Maintenance.
8 | 40569 | 4D06 | 20071001452 | AC - SPILL PREVENTION STATE | Yes |  | Construction Drawings (CD) | 51-75% | 12/2017 | 514130 | General Fund |  | Yes | On budget | No | Some site modifications complete with others in design phase; conversion to Natural Gas will allow some fuel oil storage to be eliminated; funds will be used for recurring 5-year SPCC Plan updates and continued remediation at Central Prison
9 | 40569 | 4D07 | 200510014531 | AC - UST REMOVAL | Yes |  | Final Drawings/Bid (FD) | 25-50% | 12/2017 | 237654 | General Fund |  | Yes | On budget | No | Inactive UST's have been removed at several locations but there are still many to be removed and contaminated sites to be remediated.
11 | 40692 | 4E01 | 090820701A | JJ DET&NEW HANOVER SEPTIC SYSTEM (JO 3210) | Yes | - | - | Complete | on hold | 139872 | General Fund |  | Yes | On budget | No | Juv. Justice is working a Master Plan to match facilities with future needs. Evaluating additional needs.
12 | 40692 | 4E02 | 60703901 | JJ RICHMOND ROOF & SIDEWALK&ABA TEMENT (JO 3201) | Yes | - | - | Complete | On Hold | 319847 | General Fund |  | Yes | On budget | No | Juv. Justice is working a Master Plan to match facilities with future needs. Evaluating additional needs.
13 | 40692 | 4E03 | 110907001 | JJ STONEWALL JACKSON RD REP (JO 3232) | Yes |  | Final Drawings/Bid (FD) | Complete | Warranty | 233755 | General Fund |  | Yes | On budget | No | Project complete - Last time on report
14 | 40692 | 4E04 | 60703801 | JJ NEW ROOF DOBBS CAFETERIA (JO 3200) | Yes |  | Final Drawings/Bid (FD) | Complete | on hold | 198245 | General Fund |  | Yes | On budget | No | Juv. Justice is working a Master Plan to match facilities with future needs. Evaluating additional needs.
15 | 40692 | 4E05 | 11-09072-01A | JJ DILLON HVAC PLUMBLING IMP (JO 3199) | Yes |  | Final Drawings/Bid (FD) | Complete | on hold | 346019 | General Fund |  | Yes | On budget | No | Juv. Justice is working a Master Plan to match facilities with future needs. Evaluating additional needs.
16 | 40692 | 4E06 | 200710014519 | AC - FIRE & LIFE SAFETY PROJ | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 587488 | General Fund |  | Yes | On budget | No | Funds have been used for 20 projects - 1 in progress. The projects completed include fire alarm systems, electrical panel upgrades and generators and TVSS equipment
17 | 40692 | 4E07 | 200710014513 | AC - KITCH HOOD SUPP SYS UPGR | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 118297 | General Fund |  | Yes | On budget | No | Funds have been used for 5 projects - 4 completed and 1 in progress. These are code required upgrades to existing hoods.
18 | 40692 | 4E08 | 200710014521 | AC - ROOF REP & REPLACE PROJ | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 963784 | General Fund |  | Yes | On budget | No | Nine projects have been completed. One project underway.
19 | 40692 | 4E09 | 200710014524 | AC - ENERGY EFF IMPROV PROJECTS | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 490445 | General Fund |  | Yes | On budget | No | Eleven projects have been completed. The remaining projects are under construction by Unit Maintenance.
20 | 40692 | 4E10 | 200710014530 | AC - PERIMETER FENCE SYS UPGR | Yes |  | Final Drawings/Bid (FD) | 51-75% | 07/2017 | 4601839 | General Fund |  | Yes | On budget | No | Funds have been used to complete two projects. A third project is under construction.
22 | 40692 | 4E12 | OC 25 to be revised | AC - BERTIE-ENTRPRS-PREFAB C | No |  | Design Development (DD) | - | on hold | 0 | Receipts | - | Yes | On budget | No | Project will be funded by Correction Enterprise at approved budget when funds are available.
23 | 40692 | 4E13 | 200945100145 | AC - CP HOSP SUPPLMENTL FUNDS | No | - | - | Complete | 12/2017 | 5679682 | General Fund |  | Yes | On budget | No | Work is complete. Warranty period in effect.
24 | 40798 | 4G01 | 90864501 | JJ BOILER EFFICIENCY IMPROVEMENTS (JO 3513) | Yes |  | - | Complete | 12/2017 | 124350 | General Fund |  | No | On budget | Yes | This phase complete but SCO recommended closing all projects simultaneously.
25 | 40798 | 4G03 | 20091001455 | AC - WELFARE-CALEDONIA PROG B | No | - | Design Development (DD) |  | on hold | 720 | Receipts |  | No | On budget | No | Project will be funded by Inmate Welfare Fund at approved budget when funds are available.
26 | 40798 | 4G04 | 20091001458 | AC - WELFARE-CASWELL PROG BLD | No | - | Design Development (DD) |  | on hold | 8120 | Receipts |  | No | On budget | No | Project will be funded by Inmate Welfare Fund at approved budget when funds are available.
27 | 40798 | 4G05 | 200910014524 | AC - FIRE & LIFE SAFETY PROJ | Yes | - | Construction Drawings (CD) | 76%-100% | 12/2017 | 654967 | General Fund |  | Yes | On budget | No | Funds have been used to complete 21 projects. There are 6 active projects ranging from design to construction.
28 | 40798 | 4G06 | 200910014523 | AC -KITCHEN HOOD SUPP SYS UP | Yes |  | Construction Drawings (CD) | 76%-100% | 12/2017 | 133504 | General Fund |  | Yes | On budget | No | One major hood design project complete, several minor hood design projects complete. One major hood design project under design contract. One minor repair in progress.
29 | 40798 | 4G08 | 200910014529 | AC - MECHAN SYS RENOV/REPLAC | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 447155 | General Fund |  | Yes | On budget | No | Six projects have been completed. One pending final SCO approval to be complete.
30 | 40798 | 4G09 | 200910014531 | AC - WATER/WASTEWATER IMPROVE | Yes |  | Construction Drawings (CD) | 76%-100% | 12/2017 | 1291746 | General Fund |  | Yes | On budget | No | Five projects completed. One project in progress from design to construction stage.
31 | 40798 | 4G10 | 200910014513 | AC - ENERGY EFFICIENCY IMPROV | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 486616 | General Fund |  | Yes | On budget | No | Seven projects completed. Two projects in construction stage.
33 | 40799 | 4H02 |  | Palliative Care Unit | Yes |  | Design Development (DD) | 0-25% | 01/2018 | 13120 | Debt Financed | General Fund | Yes | On budget |  | Conversion of existing Central Prison facilities for a specialized care unit - design in progress
34 | 44897 | 4K05 |  | Palliative Care Unit | Yes |  | Design Development (DD) | 0-25% | 01/2018 | 53338 | Debt Financed | General Fund | Yes | On budget |  | Conversion of existing Central Prison facilities for a specialized care unit - design in progress
35 | 40946 | 4M01 | 090820701A | JJ SEPTIC SYSTEM-NEW HANOVER (JO 3260) | Yes |  | - | - | on hold | 30445 | Debt Financed |  |  |  |  | Juv. Justice is working on a Master Plan to match facilities with future needs. Balance of funding on hold for possible re-allocation.
36 | 40946 | 4M02 |  | JJ - Western Group Home (JO 3432) | Yes |  | Final Drawings/Bid (FD) | 76%-100% | Warranty | 564667 | Debt Financed |  | No | Over budget | Yes | Project complete - Warranty stage
37 | 40946 | 4M05 | 20114510002 | AC - KITCHEN HOOD SUPP UNDRAD | Yes |  | Construction Drawings (CD) | 25-50% | 12/2017 | 272034 | Debt Financed | - | Yes | On budget | No | Two projects completed. One in construction. One still being designed.
39 |  | 4M10 |  | Palliative Care Unit | Yes |  | Design Development (DD) | 0-25% | 01/2018 | 0 | Debt Financed | General Fund | Yes | On budget |  | Conversion of existing Central Prison facilities for a specialized care unit - design in progress
40 | 41006 | 4N02 | 200910014510 | AC - WELFARE-SOUTHERN MED BLD | Yes |  |  |  | on hold | 7650 | Receipts |  |  |  |  | Project funded by Inmate Welfare Fund on hold pending funding.
41 | 41006 | 4N05 | 20134510011 | AC - R&R KITCHEN HOOD UPGRAD | Yes |  | Construction Drawings (CD) | 0-25% | 12/2017 | 135891 | General Fund |  | Yes | On budget | No | One project designed and construction beginning. One project identified and under contract for design.
42 | 41006 | 4N06 | 20134510018 | AC - R&R FIRE & LIFE SAFETY | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 68454 | General Fund |  | Yes | On budget | No | Six projects completed. Balance to be assigned to other projects.
43 | 41006 | 4N07 | 20134510013 | AC - ROOF REPAIRS & REPLACE | Yes |  | Final Drawings/Bid (FD) | Complete | 12/2017 | 167767 | General Fund |  | Yes | On budget | No | Four projects complete.
44 | 41006 | 4N08 | NA | AC - ENTERPRISE-AHU'S FOR SAMP LAUNDRY (JO 3098) | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 359591 | Receipts |  | Yes | On budget | No | Project funded by Correction Enterprise receipts. Work in progress to correct duct issues.
45 | 41166 | 4P01 | 110907001 | JJ STONEWALL JACKSON R&R (JO 3206) | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 2223612 | General Fund |  | No | On budget | No | All construction work complete. Warranty period and final work by Regional/Unit Maintenance to be completed.
46 | 41166 | 4P02 | 11-09072-01A | JJ CA DILLON R&R (JO 3187) | Yes |  | Final Drawings/Bid (FD) | Complete | Warranty | 1432392 | General Fund |  | Yes | On budget | No | Construction complete. Warranty issues resolved. Ready to be closed.
47 | 41207 | 4U08 | 120895701 | JJ Track & Field Facility - Stonewall Jackson YDC (JO 3223) | Yes | - | Construction Drawings (CD) | 0-25% | 12/2017 | 149255 | Receipts |  | Yes | Over budget | Yes | Under contract - scope reduction required to complete track work with buildings as designed.
48 | 41207 | 4U09 | 20134510011 | AC Kitchen Hood Upgrade | Yes | - | Construction Drawings (CD) | 0-25% | 12/2017 | 37438 | General Fund |  | Yes | On budget | No | One design @ SCO for approval. Three under construction at various levels of completion. One complete.
49 | 41207 | 4U10 | 20134510017 | AC Obsolete Electronic Systems | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 1151330 | General Fund |  | Yes | On budget | No | Five projects completed. Three projects in progress from design to final completion.
50 | 41207 | 4U11 | 20134510018 | AC Fire & Life Safety Projects | Yes | - | Construction Drawings (CD) | 25-50% | 12/2017 | 760698 | General Fund |  | Yes | On budget | No | Five projects in progress at different stages from design to construction. Two projects complete.
51 | 41207 | 4U12 | 20134510019 | AC CP Elevators (JO 3245) | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 06/2017 | 1050351 | General Fund |  | Yes | On budget | No | Upgrade work on designated elevators complete. Balance remaining will be used toward other elevator work.
52 | 41207 | 4U13 | 20134510013 | AC Roof Repair & Replacement | Yes | - | Construction Drawings (CD) | 51-75% | 12/2017 | 1404061 | General Fund |  | Yes | On budget | No | Eleven Projects completed. Seven other projects in progress.
53 | 41207 | 4U14 | 201345100110 | AC Mechanical Systems Renov. & Replace. | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 1375179 | General Fund |  | Yes | On budget | No | Twelve Projects completed. Three projects in progress at different stages of construction.
54 | 41207 | 4U15 | 20134510011 | AC Water/Wastewater Improvements | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 12/2017 | 747823 | General Fund |  | Yes | On budget | No | Systems upgrade at as many facilities as funding will support. Some have been designed by CE staff while others are by contract. Construction is through a combination of CM&M (ICP), Regional Maintenance and/or contract.
55 | 41207 | 4U16 | 20134510012 | AC DART Cherry Renovations (JO 3288) | Yes | - | Construction Drawings (CD) | 76%-100% | 12/2017 | 70491 | General Fund |  | Yes | On budget | No | Restoration project to restore space in an existing building to use as a maintenance shop, storage and general purposes.
56 | 41207 | 4U17 | 20134510014 | AC Energy Efficiency Impv. Projects | Yes | - | Final Drawings/Bid (FD) | 25-50% | 12/2017 | 472296 | General Fund |  | Yes | On budget | No | One project completed. Seven projects in progress.
57 | 41207 | 4U18 | 20134510015 | AC Asbestos Abatement & Haz. Materials | Yes | - | - | - | 12/2017 | 76170 | General Fund |  | Yes | On budget | No | Multiple projects completed. Identifying other work to remediate.
58 | 41207 | 4U19 | 20134510016 | AC Underground Storage Tank (UST) Removal | Yes | - | - | - | 12/2017 | 16957 | General Fund |  | Yes | On budget | No | Executing plans to remove identified UST's based on priority throughout the Department
59 | 41207 | 4U20 | 201149400294 | EM Badin Warehouse Repairs (JO 3284) | Yes | - | Final Drawings/Bid (FD) | Complete | 05/2015 | 162267 | General Fund |  | Yes | On budget | No | Work complete - warranty period.
60 | 41207 | 4U21 | 20114940022 | EM Badin Warehouse ADA (JO 3287) | Yes | - | Final Drawings/Bid (FD) | Complete | 05/2015 | 71971 | General Fund |  | Yes | On budget | No | Work complete - warranty period.
61 | 41207 | 4U23 | 20115120115 | JJDP Dillon Fire Alarm & Water Pressure (JO 3246) | Yes | - | - | - | on hold | 33173 | General Fund |  | Yes | On budget | No | Juv. Justice is working a Master Plan to match facilities with future needs. Evaluating additional needs.
62 | 41207 | 4U24 | 20115120114 | JJDP YDC Security Cameras & Surveillance | Yes | - | Construction Drawings (CD) | 25-50% | 12/2017 | 882484 | General Fund |  | Yes | On budget | No | Work has been completed at CA Dillon YDC and Pitt JDC. Regional Maintenance working at Dobbs and ICP will complete Stonewall Jackson YDC. ECS working at Cumberland JDC
63 | 41207 | 4U25 | 201151201111 | JJDP Dobbs HVAC & Mechanical Upgrades (JO 3247) | Yes | - | - | - | on hold | 27393 | General Fund |  | Yes | On budget | No | Juv. Justice is working a Master Plan to match facilities with future needs. Evaluating additional needs.
64 | 41207 | 4U26 | 20115120113 | JJDP YDC Safety & Security Systems | Yes | - | Final Drawings/Bid (FD) | 51-75% | 12/2017 | 159986 | General Fund |  | Yes | On budget | No | Three projects complete and one in progress.
65 | 41207 | 4U27 |  | NG Fire Alarm Systems - Phase 2 | Yes |  | Design Development (DD) | Complete | 06/10/2015 | 57319 | General Fund |  | Yes | On budget | No | Awaiting final walkthrough
66 | 41207 | 4U28 | 20134940032 | SHP Renovations & Repairs - Asheboro (JO 3285) | Yes | - | - | Complete | Warranty | 174171 | General Fund |  | Yes | On budget | No | Remodel complete. Warranty period complete. Last time on report.
67 | 41207 | 4U30 |  | SHP Training Academy Bldg. 10 (JO 3376) | Yes | - | - | Complete | Warranty | 982657 | General Fund |  | Yes | On budget | No | Initial renovations complete - looking at additional needs to utilize funds.
68 | 44365 | 4B02 | NA | JJ DOBBS COTT/GYM/SCH HVAC (JO 3203) | Yes |  | - | Complete | on hold | 263088 | Debt Financed |  | Yes | On budget | No | Juv. Justice is working a Master Plan to match facilities with future needs. Evaluating additional needs.
69 | 44365 | 4B04 | 200510014516 | AJ - FIRE & LIFE SAFETY | Yes |  | Final Drawings/Bid (FD) | 51-75% | 12/2017 | 1494117 | Debt Financed | - | Yes | On budget | No | Funded replacement of Fire Alarm Systems & Fire Protection Systems at Central Prison and other facilities. Six projects in progress. Seven complete.
70 | 44365 | 4B05 | 200510014517 | AJ - ROOF REPAIRS & REPLACE | Yes |  | Final Drawings/Bid (FD) | 0-25% | ONGOING | 4729053 | Debt Financed | - | Yes | On budget | No | Multiple Locations completed. Two projects to be completed.
71 | 44365 | 4B06 |  | NG FIRE ALARM SYSTEMS - PHASE II | Yes | - | Final Drawings/Bid (FD) | 51-75% | 12/2015 | 1064011.88 | Debt Financed |  | Yes | On budget | No | Design complete. All current projects Construction awarded.
72 | 44896 | 4J01 | 20091005452 | AJ - BROUGHTON STEAM PLT-ENT (JO 2891) | Yes |  | Construction Drawings (CD) | 0-25% | 06/2017 | 2943721 | Receipts |  | Yes | On budget | No | Construction is 98% complete with minor adjustments to be completed during warranty phase.
73 | 44896 | 4J04 | OC 25 to be revised | AJ - TABOR INDUSTRY UPFIT-ENT (JO 3595) | No |  | Design Development (DD) | 0-25% |  | 0 | Receipts |  | Yes | On budget | No | Project will be funded by Correction Enterprise receipts. Funded at $2,123,000.
74 | 44896 | 4J05 |  | NG - Master Plan Statewide Ph 2 | Yes | - | Design Development (DD) | 51-75% | ONGOING | 529475 | General Fund | - | Yes | - | No | Ongoing designs for all HUBs
75 | 44896 | 4R14 | 13-10168-01 | NG - Electronic Simulation | No | - | Final Drawings/Bid (FD) | Complete | 05/2014 | 50630 | Receipts | - | Yes | On budget | No | Under construction contract.
76 | 41307 | 4R15 | 11-09317-01 | NG - Fire Bucket Storage | No | - | Final Drawings/Bid (FD) | Complete | 06/2014 | 227767.76 | Receipts | - | Yes | On budget | No | Under construction contract.
77 | 41307 | 4R16 | 12-09335-01 | NG - Camp Butner Big Top | No | - | Final Drawings/Bid (FD) | Complete |  | 559940 | Receipts | - | Yes | On budget | No | Under design contract - waiting on federal funds
78 | 41307 | 4R17 | 201370920122 | AJ - Samarcand Training Academy (JO 3363 & 3536) | Yes | - | Construction Drawings (CD) | 51-75% | 2017-12-01 | 5204928 | General Fund |  | No | On budget | Yes | Construction moving along on buildings to be renovated in this phase.
79 | 41307 | 4R18 |  | NG Projects | Yes | - | Final Drawings/Bid (FD) |  |  | 0 | General Fund
80 | 41307 | 4R19 | 13-09999-04 A | NG - Wilmington Building Expansion | Yes |  | Final Drawings/Bid (FD) | 0-25% | on hold | 103706 | General Fund | Receipts | Yes | On budget |  | Under design contract/Construction cancelled
81 | 41307 | 4R20 | 13-09999-04 B | NG - Wilmington Site Expansion |  |  | Final Drawings/Bid (FD) | 51-75% | 2017-01-01 | 990141 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
82 | 41307 | 4R21 | 13-09999-02 E | NG - Nashville Building Expansion | Yes |  | Final Drawings/Bid (FD) | 0-25% | 2017-01-01 | 97675 | General Fund | Receipts | Yes | On budget |  | Under design contract.
83 | 41307 | 4R22 | 13-09999-02 F | NG - Nashville Site Expansion |  |  | Final Drawings/Bid (FD) | 0-25% | 2017-01-01 | 84814 | General Fund | Receipts | Yes | On budget |  | Under design contract.
84 | 41307 | 4R23 | 13-09999-04 C | NG - Clinton Building Expansion | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 2017-01-01 | 450425.22 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
85 | 41307 | 4R24 | 13-09999-04 D | NG - Clinton Site Expansion |  |  | Final Drawings/Bid (FD) | 76%-100% | 2017-01-01 | 991610.46 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
86 | 41307 | 4R25 | 13-09999-01 E | NG - Salisbury Building Expansion | Yes |  | Final Drawings/Bid (FD) | 0-25% | on hold | 97650 | General Fund | Receipts | Yes | On budget |  | Under design contract.
87 | 41307 | 4R26 | 13-09999-01 F | NG - Salisbury Site Expansion |  |  | Final Drawings/Bid (FD) | 51-75% | 2017-01-01 | 836397.17 | General Fund | Receipts | Yes | On budget |  | Under design contract.
88 | 41307 | 4R27 | 13-09999-01 C | NG - Parkton Building Expansion | Yes |  | Final Drawings/Bid (FD) | 0-25% | 2017-01-01 | 97540 | General Fund | Receipts | Yes | On budget |  | Under design contract.
89 | 41307 | 4R28 | 13-09999-01 D | NG - Parkton Site Expansion |  |  | Final Drawings/Bid (FD) | 0-25% | 2017-01-01 | 90747 | General Fund | Receipts | Yes | On budget |  | Under design contract.
90 | 41307 | 4R29 | 13-09999-02 C | NG - Benson Building Expansion | Yes |  | Final Drawings/Bid (FD) | 0-25% | 2017-01-01 | 98223 | General Fund | Receipts | Yes | On budget |  | Under design contract.
91 | 41307 | 4R30 | 13-09999-02 D | NG - Benson Site Expansion |  |  | Final Drawings/Bid (FD) | 0-25% | 2017-01-01 | 84764 | General Fund | Receipts | Yes | On budget |  | Under design contract.
92 | 41307 | 4R31 | 13-09999-03 D | NG - Charlotte Building Expansion | Yes |  | Final Drawings/Bid (FD) | complete | 2015-10-19 | 1169779.23 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
93 | 41307 | 4R32 | 13-09999-01 A | NG - Asheboro Site Expansion |  |  | Final Drawings/Bid (FD) | 76%-100% | 2017-01-01 | 1027467.68 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
94 | 41307 | 4R33 | 13-09999-01 G | NG - Winston-Salem Building Expansion | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 2016-11-01 | 1204614.85 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
95 | 41307 | 4R34 | 13-09999-01 H | NG - Winston-Salem Site Expansion |  |  | Final Drawings/Bid (FD) | 76%-100% | 2016-11-01 | 1108111.57 | General Fund | Receipts | Yes | On budget |  | Under design contract.
96 | 41307 | 4R35 | 13-09999-03 B | NG - Concord Building Expansion | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 2017-01-01 | 1194320.57 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
97 | 41307 | 4R36 | 13-09999-03 C | NG - Concord Site Expansion |  |  | Final Drawings/Bid (FD) | 76%-100% | 2016-12-01 | 948491.41 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
120 | 41307 | 4R37 | 13-09999-01 B | NG - Burlington Site Expansion |  |  | Final Drawings/Bid (FD) | 51-75% | 2015-09-01 | 1195729 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
121 | 41307 | 4R38 | 13-09999-03 A | NG - Albemarle Site Expansion |  |  | Final Drawings/Bid (FD) | 51-75% | 2017-01-01 | 1171905 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
98 | 41307 | 4R39 | 13-09999-03 E | NG - Belmont Building Rehab | Yes |  | Final Drawings/Bid (FD) | 0-25% | on hold | 99527 | General Fund | Receipts | Yes | On budget |  | Under design contract.
99 | 41307 | 4R40 | 13-09999-04 E | NG - Beulaville Building Expansion | Yes |  | Final Drawings/Bid (FD) | 0-25% | on hold | 88270 | General Fund | Receipts | Yes | On budget |  | Under design contract.
100 | 41307 | 4R41 | 13-09999-05 | NG - Boone Building Expansion | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 2016-12-01 | 1161254 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
101 | 41307 | 4R42 | 13-09999-02 B | NG - Dunn Building Expansion | Yes |  | Final Drawings/Bid (FD) | Complete | 2017-08-01 | 93132 | General Fund | Receipts | Yes | On budget |  | Under design contract.
102 | 41307 | 4R43 | 13-09999-02 A | NG - Durham Building Expansion | Yes | - | Final Drawings/Bid (FD) | Complete | 2016-05-01 | 1188577 | General Fund | Receipts | Yes | On budget |  | Under construction contract.
103 | 41307 | 4R44 | 20137092011 | AJ - Kitchen Hood Suppression Systems | Yes | - | Design Development (DD) | 0-25% | 2017-12-01 | 275186 | General Fund |  | Yes | On budget | No | Five projects identified. One contracted for design.
104 | 41307 | 4R45 | 20137092012 | AJ - Replace/Upgrade Obsolete Electronic Systems | Yes | - | Construction Drawings (CD) | 25-50% | 2017-12-01 | 1331069 | General Fund |  | Yes | On budget | No | Ten projects identified. Four completed and work has begun on 6 other projects.
105 | 41307 | 4R46 | 20137092013 | AJ - Fire & Life Safety Systems | Yes | - | Design Development (DD) | 0-25% | 2017-12-01 | 489789 | General Fund |  | Yes | On budget | No | Nineteen projects funded. Seven completed. Twelve in design or construction.
106 | 41307 | 4R47 | 20137092014 | AJ - Roof Repair & Renovation | Yes | - | Construction Drawings (CD) | 51-75% | 2017-12-01 | 5233129 | General Fund |  | Yes | On budget | No | Eighteen projects identified. Six completed. Twelve in progress our under design.
107 | 41307 | 4R48 | 201370920117 | AJ - Architectural Systems | Yes | - | Design Development (DD) | 0-25% | 2017-12-01 | 107737 | General Fund |  | Yes | On budget | No | Ten projects completed with 8 in progress and remainder in design.
108 | 41307 | 4R49 | 20137092022 | AJ - Juvenile Justice Strategic Plan | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 2017-12-01 | 1611238 | General Fund |  | Yes | On budget | No | Implementation of Long Range Strategic Plan - renovations at Stonewall Jackson and expansions at Lenoir, Edgecombe and Chatham. SJ/McWhorter complete; Edgecombe & Lenoir in warranty phase; Chatham on hold.
109 | 41307 | 4R50 | 201349400410 | NG - Reno to Improve Existing | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 2016-09-30 | 1834390 | General Fund | Receipts | Yes | On budget
110 | 41307 | 4R51 | 201349400411 | NG - Mechanical System Reno | Yes | - | Final Drawings/Bid (FD) | 76%-100% | 2016-09-30 | 1513008 | General Fund | Receipts | Yes | On budget
111 | 41307 | 4R52 | 201349400412 | NG - Fire & Lyfe Safety Systems | Yes | - | Final Drawings/Bid (FD) | Complete | 2016-04-30 | 218540 | General Fund | Receipts | Yes | On budget
112 | 41307 | 4R53 | 201349400417 | NG - Deteriorated Fences | Yes | - | Final Drawings/Bid (FD) | Complete | 2015-06-01 | 48000 | General Fund | Receipts | Yes | On budget
113 | 41307 | 4R54 | 201349400420 | NG - Water & Waste Water Improvements | Yes | - | Final Drawings/Bid (FD) | Complete | 2016-08-30 | 87000 | General Fund | Receipts | Yes | On budget
114 | 41307 | 4R55 | 20134940049 | NG - Underground Storage | Yes | - | Design Development (DD) | 0-25% | 2017-06-01 | 18148.09 | General Fund | Receipts | Yes
115 | 41307 | 4R56 | 201349400421 | NG - Security Systems | Yes | - | Construction Drawings (CD) | 0-25% | 2015-02-01 | 17624 | General Fund | Receipts | Yes
116 | 41307 | 4R58 | 20137092042 | EM - Badin Warehouse - Access (JO 3394) | Yes | - | - | Complete | 2015-05-01 | 85015 | General Fund |  | Yes | On budget | No | Work complete - warranty period.
117 | 41307 | 4R59 | 20134940031 | SHP - Laurinburg Office Renovations | Yes | - | - | Complete | 2016-10-01 | 42000 | General Fund |  | Yes | On budget | No | Work is complete. Warranty period in effect.
118 | 41307 | 4R60 |  | AJ-Multipurpose Group Home (JO 3436) | Yes | - | Final Drawings/Bid (FD) | Complete | 03/2016 | 599674 | General Fund |  | Yes | On budget | No | Work is complete. Warranty period in effect.
119 | 41307 | 4R61 | 20113650029 | SBI - Bldg. 9 Renovations (JO 3490) | Yes |  | Final Drawings/Bid (FD) | Complete | 2016-05-01 | 1092833 | General Fund |  |  |  |  | Work complete - warranty period.
120 | 41307 | 4R62 | 201341101345 | SBI - Bldg. 16 Renovations (JO 3491) | Yes |  | Design Development (DD) | 0-25% | 2016-08-01 | 438037 | General Fund |  |  |  |  | Design is complete. Awaiting funding for construction to begin
121 | 41307 | 4T01 |  | NG - State Match Fund | Yes |  |  |  |  | 3250000 | General Fund | Receipts
122 | 41407 | 4T02 |  | Caledonia Grain Bin | No |  | Design Development (DD) |  | 2017-07-01 | 23988 | Receipts |  |  |  |  | Working with vendor to supply unit(s) and preliminary design/surveys.
123 | 41407 | 4T03 |  | Maury Industry Upfit | No |  |  |  | on hold | 0 | Receipts |  |  |  |  | Scope has not been defined by owner
124 | 41407 | 4S01 | 20157092001 | AJ - Samarcand Training Academy (JO 3503) | Yes |  | Construction Drawings (CD) | 51-75% | 2017-12-01 | 4512442 | Debt Financed |  |  |  |  | Construction moving along on buildings to be renovated in this phase.
125 | 41446 | 4S02 | 20157092014 | AJ - Replace/Upgrade Obsolete Electronic Systems | Yes |  | Construction Drawings (CD) | 25-50% | 2017-12-01 | 496089 | Debt Financed |  |  |  |  | One project complete. One designed and in procurement.
126 | 41446 | 4S03 | 201370920129 | AJ - Mechanical Systems R&R | Yes |  | Design Development (DD) | 0-25% | 2017-12-01 | 774145 | Debt Financed |  |  |  |  | Three projects completed. Eight projects defined and in design.
127 | 41446 | 4S04 | 201370920135 | AJ - Fire & Life Safety | Yes |  | Design Development (DD) | 0-25% | 2017-12-01 | 91 | Debt Financed |  |  |  |  | Two projects defined and in design.
128 | 41446 | 4S05 | 201370920128 | AJ - Roof Repair & Replacement | Yes |  | Design Development (DD) | 0-25% | 2017-12-01 | 209854 | Debt Financed |  |  |  |  | Four projects defined and in design
129 | 41446 | 4S06 | 201370920136 | AJ - Architectural Systems | Yes |  | Design Development (DD) | 0-25% | 2017-12-01 | 132723 | Debt Financed |  |  |  |  | Two projects completed. Five projects in design.
130 | 41446 | 4S07 | 201370920130 | AJ - Asbestos Abatement & Haz. Mat. | Yes |  | Design Development (DD) | 0-25% | 2017-12-01 | 100690 | Debt Financed |  |  |  |  | Four projects complete. Two other projects in progress.
131 | 41507 | 4Q01 |  | AC - Palliative Care Unit (JO 3572) | Yes |  | Design Development (DD) | 0-25% | 01/2018 | 0 | General Fund | General Fund | Yes | On budget |  | Conversion of existing Central Prison facilities for a specialized care unit - design in progress
132 | 41507 | 4Q02 |  | NG-Armory & Facility Development | [5 empty] | 7100 | General Fund |  |  |  |  | Funding not available until July, 2016
133 | 41507 | 4Q04 | 20157092014 | AJ - Replace/Upgrade Obsolete Electronic Systems | Yes | N | Final Drawings/Bid (FD) | 25-50% | 01/01/2018 | 649327 | General Fund |  |  |  |  | Seven projects designed and beginning installation
134 | 41507 | 4Q05 | 201370920135 | AJ - Fire & Life Safety Systems | Yes | N | Design Development (DD) | 0-25% | 07/01/2018 | 0 | General Fund |  |  |  |  | Ten projects defined and in design
135 | 41507 | 4Q06 | 201370920136 | AJ - Architectural Systems | Yes | N | Design Development (DD) | 0-25% | 07/01/2018 | 806 | General Fund |  |  |  |  | Nine projects defined and in design
136 | 41507 | 4Q07 | 201370920130 | AJ - Asbestos Abatement & Haz. Mat. | Yes | N | Design Development (DD) | 0-25% | 07/01/2018 | 56587 | General Fund |  |  |  |  | One project completed. Balance to be used as part of Samarcand Trng. Academy Renovations
137 | 41507 | 4Q08 | 201370920131 | AJ - Water & Wastewater Treatment | Yes | N | Design Development (DD) | 0-25% | 07/01/2018 | 6900 | General Fund |  |  |  |  | One project defined and in design
138 | 41507 | 4Q09 | 201370920133 | AJ - Energy Efficiency Projects | Yes | N | Design Development (DD) | 0-25% | 07/01/2018 | 2017 | General Fund |  |  |  |  | One project defined and in progress
139 | 41507 | 4Q10 | 20157092013 | AJ - Kitchen Hood Suppression Systems | Yes | N | Design Development (DD) | 0-25% | 07/01/2018 | 0 | General Fund
140 | 41507 | 4Q11 | 20137092019 | AJ - Underground Storage Tanks | Yes | N | Design Development (DD) | 0-25% | 07/01/2018 | 0 | General Fund |  |  |  |  | Contract issued for site analysis to remove tanks as funding allows.
141 | 41507 | 4Q12 | 20157092012 | AJ - Demolition of Abandoned Bldgs | Yes | N | Design Development (DD) | 0-25% | 07/01/2018 | 0 | General Fund |  |  |  |  | Two projects defined and in progress
142 | 41507 | 4Q13 | 20157092011 | AJ - Paving Repairs, Chase Roads, etc. | Yes | N | Design Development (DD) | 0-25% | 07/01/2018 | 0 | General Fund |  |  |  |  | One project identified and in design stage.
143 | 41507 | 4Q14 | 201370920134 | AJ - Security Fencing | Yes | N | Design Development (DD) | 0-25% | 07/01/2018 | 0 | General Fund
144 | 41507 | 4Q15 | 201370920522 | NG-Renovate - Improve Space | Yes | N |  |  |  | 24915 | General Fund
145 | 41507 | 4Q16 | 201370920525 | NG-Fire & Life Safety Systems | Yes | N |  |  |  | 0 | General Fund
146 | 41507 | 4Q17 | 201370920523 | NG-Electrical, Plumbing & HVAC | Yes | N |  |  |  | 0 | General Fund
147 | 41507 | 4Q18 | 201370920521 | NG-Roof Repair & Replacement | Yes | N |  |  |  | 0 | General Fund
148 | 41507 | 4Q19 | 201370920524 | NG-Asbestos Abatement & Haz. Mater. | Yes | N |  |  |  | 0 | General Fund
149 | 41507 | 4Q20 | 20137092043 | EM - Badin Warehouse - LT Access & Paving (JO 3616) | Yes | N | Design Development (DD) | 0-25% | 07/01/2018 | 14253 | General Fund |  |  |  |  | Contracting for Civil Eng. Evaluation & recommendation
150 | 41507 | 4Q21 | 201149400312 | SHP - Lincolnton Office | Yes | N | Final Drawings/Bid (FD) | 76%-100% |  | 26218 | General Fund |  |  |  |  | 90% complete. Resolving issues with Contractor.
151 | 41507 | 4Q22 | 20114940034 & 201149400311 | SHP - Fuel Master Monitors |  |  |  | 51-75% |  | 292046.93 | General Fund |  |  |  |  | 32 of 60 sites complete. Equipment ordered for next 15 sites.
152 | 41507 | 4Q23 |  | AJ - Nash CI - Generator Replacement (JO 3627) | Yes | N | Construction Drawings (CD) | 51-75% | 07/01/2018 | 0 | General Fund |  |  |  |  | Project under design by Contractor
153 | 41507 | 4Q24 | 201370920129 | AJ - Mechanical Systems R&R | Yes | N | Design Development (DD) | 0-25% | 07/01/2018 | 815499 | General Fund |  |  |  |  | Eleven projects definded and under design
154 | 41507 | 4Q25 | 201370920128 | AJ - Roof Repair & Replacement | Yes | N | Design Development (DD) | 0-25% | 07/01/2018 | 116 | General Fund |  |  |  |  | Ten projects identified and in various planning or intallation stages.
155 | 41607 | 4601 | 20177092012 | AJ - Nash Print Plant Roof Repl. | Yes | N | Design Development (DD) |  | 07/01/2018 | 0 | Receipts |  |  |  |  | Replacement of the Print Plant Roof funded by Correction Enterprise. To be coordinated with other roof work at Nash CI
156 | 41607 | 4602 | 20177092013 | AJ - Harnett Visitor Center | Yes | N | Design Development (DD) |  | 07/01/2018 | 5479 | Receipts |  |  |  |  | Visitor center to be added as part of perimeter fence replacement. Funded through Inmate Welfare.
| 41607 | 4604 |  | NG - Armry & Fclty Dev - Eliz | [5 empty] | 0 | General Fund | Receipts
| 41607 | 4605 |  | NG - Armry & Fclty Dev - JAC | [5 empty] | 0 | General Fund | Receipts
| 41607 | 4606 |  | NG - Armry & Fclty Dev - LOU | [5 empty] | 0 | General Fund | Receipts
| 41607 | 4607 |  | NG - Armry & Fclty Dev - REIDS | [5 empty] | 0 | General Fund | Receipts
| 41607 | 4608 |  | NG - Helipad Planning | [5 empty] | 0 | General Fund | Receipts
| 41607 | 4609 |  | NG - Camp Butner Land Purchase | [5 empty] | 0 | General Fund | Receipts
| 41607 | 4610 |  | NG - Wilkes Cty Armory Sup | [5 empty] | 0 | General Fund | Receipts
| 41607 | 4611 |  | NG - Tarheel Challenge Gym | [5 empty] | 0 | General Fund | Receipts
| 41607 | 4612 |  | AJ - Piedmont CI Elevator R&R |  |  | Design Development (DD) |  | 07/01/2018 | 0 | General Fund |  |  |  |  | Critical repairs to continue facility operations.
| 41607 | 4613 |  | Caledonia CI - Shower & Bath R&R |  |  | Final Drawings/Bid (FD) |  | 07/01/2018 | 0 | General Fund
| 41607 | 4614 |  | AJ - Energy Efficiency Projects |  |  |  |  | 07/01/2018 | 0 | General Fund
| 41607 | 4615 |  | SBI/SHP - Renovate Perimeter |  |  | Design Development (DD) |  | 07/01/2018 | 0 | General Fund |  |  |  |  | These three projects will improve overall conditions at the Garner Road Campus housing the State Highway Patrol Training Academy and offices for the State Bureau of Investigation
| 41607 | 4616 |  | SHP/SBI - Roadway & Access |  |  | Design Development (DD) |  | 07/01/2018 | 0 | General Fund
| 41607 | 4617 |  | SHP/SBI - Partial Infrastructure Rehab |  |  | Design Development (DD) |  | 07/01/2018 | 0 | General Fund
| 41607 | 4618 |  | SHP - Update Fuel Facilities |  |  |  | 0-25% |  | 0 | General Fund |  |  |  |  | Funding will continue upgrades to remaining 20+ sites.
| 41607 | 4619 |  | NG - Fire & Life Safety Systems | [5 empty] | 0 | General Fund | Receipts
| 41607 | 4620 |  | NG - Asbestos, Lead PN | [5 empty] | 0 | General Fund | Receipts
157 | 46607 | 4W01 |  | AJ - Samarcand Trng. Academy (JO 3651) | Yes | N | Construction Drawings (CD) | 0-25% | 07/01/2018 | 273907 | Debt Financed |  |  |  |  | Funding under NC Connect Bonds to continue rehabilitation of Samarcand facility
158 | 46607 | 4W02 |  | NG - Guilford Readiness Center | Yes | N |  |  |  | 0 | Debt Financed | Receipts | Yes
159 | 46607 | 4W03 |  | NG - Burke Readiness Center | Yes | N |  |  |  | 21800 | Debt Financed | Receipts | Yes
160 | 46607 | 4W04 |  | NG - Wilkes Readiness Center | Yes | N |  |  |  | 0 | Debt Financed | Receipts | Yes
[10 empty] | 0 | General Fund

## Sheet2
-
Schematic Design (SD)
Design Development (DD)
Construction Drawings (CD)
Final Drawings/Bid (FD)
-
0-25%
25-50%
51-75%
76%-100%
Complete
-
Yes
No
-
General Fund
Receipts
Debt Financed
Self-Liquidating/Revenue Bonds
-
General Fund
Receipts
Debt Financed
Self-Liquidating/Revenue Bonds
-
On budget
Under budget
Over budget
-
General Fund
Receipt
-
Appraisal
Price negotiations
COS approval process
Closing
Complete